## How to Use
SAP UAT Template
1. Test Plan: fill this in first. Scope, systems, cycles, entry and exit criteria, severity definitions and named owners.
2. Test Scripts: 24 example scenarios across FI/CO, MM, SD and HR/Payroll. Each has numbered steps with an expected result. Testers fill in Actual result, Evidence, Status, Defect ID, Tester and Date.
3. Defect Log: log every failed or blocked step here during each cycle. DEF-001 to DEF-030 are pre-numbered. Status values are listed beside the log.
4. Sign-Off: one row per process. Complete it at the end of the final cycle and use the go-live readiness block for the steering committee decision.
Order of work: plan first, then scripts, log defects during each cycle, sign-off at the end.
Scripts must be run by business users with their real production roles. Never test with SAP_ALL or a developer or basis user.
Record a document number in the Evidence column for every posting step, so a reviewer can find it in the system.
Status values for script steps: Passed, Failed, Blocked, Not run. Raise a defect for every Failed or Blocked step and note its Defect ID.
The example scripts are a starting point. Replace the placeholder IDs, processes, data and roles with your own, and delete scenarios you do not use.
Placeholder IDs used throughout: customer 100234, supplier 200150, material FG-2201, plant 1000, company code 1000, cost centre 4100. Swap in real master data from your UAT client.
From LogicHive: logic-hive.co.uk

## Test Plan
Field | Guidance | Your entry
Project name | The name the steering committee uses for the programme.
SAP release | S/4HANA, ECC 6.0 or S/4HANA Cloud. Include the release or feature pack level.
UAT system and client | For example QAS client 300. Confirm it is separate from SIT and development.
In-scope processes | Procure to pay, order to cash, record to report, hire to retire. List sub-processes and variants.
Company codes and plants in scope | List each company code and plant that will be tested.
Interfaces in scope | Banks, payroll providers, HMRC, EDI partners, third-party systems. Note the connection method.
Out of scope | Anything deliberately not tested, with the reason and who accepted the risk.
UAT cycles and dates | Cycle 1: core processes. Cycle 2: variants and exceptions. Cycle 3: regression and final run. Give start and end dates for each.
Entry criteria | SIT complete with no open critical defects. QAS refreshed with latest transports and mock migration data. Testers have production-equivalent roles. Posting periods open. Interfaces connected.
Exit criteria | All planned scripts executed. No open critical or high defects without an agreed workaround. Every process owner has signed off.
Transport freeze date | After this date only agreed defect fixes are transported into the UAT system.
Defect severity definitions | See the severity table below. Agree it with the process owners before cycle 1.
Daily defect triage time and attendees | For example 09:30 daily, test manager, process owners, functional consultants, basis contact.
Test manager | Name and contact details.
Testers by process | One named business user per process as a minimum, plus a backup.
Sign-off owner by process | The person with authority to accept each process for go-live.
Severity | Definition | SAP example
Critical | Blocks a core process or causes financial, legal or data loss with no workaround. | Payment run produces a wrong bank file or posts to the wrong GL account.
High | A main function fails and there is no practical workaround, or the workaround is unacceptable at volume. | Invoice blocks for every price variance, no workaround.
Medium | A function is impaired but a workable workaround exists. | A report field is missing but the data can be read from the document.
Low | Cosmetic or minor issue with no effect on the result. | A label or layout issue on an output form.

## Test Scripts
Script ID | Process | Module | Scenario | Preconditions | Test data | Role | Step | Action (transaction or Fiori app) | Expected result | Actual result | Evidence (document no.) | Status | Defect ID | Tester | Date
FI-01 | Record to report | FI/CO | Post a manual GL journal with cost centre and profit centre (FB50 or the Post General Journal Entries app) | Posting period open. GL accounts and cost centre 4100 active. | Company code 1000, cost centre 4100, GBP 1,250.00, expense and accrual GL accounts from your chart of accounts | GL accountant | 1 | FB50 or Post General Journal Entries app: enter header with today's posting date, currency GBP, reference | Header accepted with no error and document date and posting date populated
[7 empty] | 2 | Enter a debit line to the expense GL account with cost centre 4100 and a credit line to the accrual GL account for GBP 1,250.00 | Profit centre derives from cost centre 4100. Balance shows 0.00 before posting
[7 empty] | 3 | Post the journal | Message confirms the document number. Document type and company code 1000 are correct
[7 empty] | 4 | FB03: display the document, then KSB1 for cost centre 4100 | Both lines are present. GBP 1,250.00 appears as an actual line item on cost centre 4100
FI-02 | Record to report | FI/CO | Run the supplier payment run and check the bank file and clearing (F110) | Approved supplier invoice open and due. Payment method and house bank configured. | Supplier 200150, one open invoice GBP 4,800.00 incl. VAT, company code 1000 | Accounts payable accountant | 1 | F110: enter run date and identification, then enter parameters for company code 1000, payment method and supplier 200150 | Parameters saved and status shows parameters entered
[7 empty] | 2 | Run the proposal and review the payment proposal list | Invoice appears in the proposal for GBP 4,800.00 with the correct payment method and house bank. No blocked or exception items for this supplier
[7 empty] | 3 | Schedule the payment run and create the payment media | Run status shows payment run complete. Payment document created and invoice cleared
[7 empty] | 4 | Open the bank file output and compare to the payment list | File contains one payment for supplier 200150, GBP 4,800.00, with the correct sort code and account number
[7 empty] | 5 | FBL1N: display supplier 200150 line items | Invoice shows as cleared with a clearing document number. Open balance is GBP 0.00
FI-03 | Record to report | FI/CO | Post an incoming customer payment and clear the open invoice (F-28) | Open customer invoice exists and the bank GL account is set up. | Customer 100234, open invoice GBP 2,400.00 incl. VAT, bank GL account from your chart of accounts | Accounts receivable accountant | 1 | F-28: enter document date, company code 1000, currency GBP, amount 2,400.00, bank account and customer 100234 | Header accepted and open items selection is available
[7 empty] | 2 | Process open items and select the invoice | Invoice is selected for GBP 2,400.00 and the not assigned amount shows 0.00
[7 empty] | 3 | Post the payment | Message confirms the document number. Debit to bank GL account and credit to customer 100234
[7 empty] | 4 | FBL5N: display customer 100234 line items including cleared items | Invoice and payment both show cleared with the same clearing document. Open balance is GBP 0.00
FI-04 | Record to report | FI/CO | Month-end GR/IR clearing and foreign currency revaluation (F.13, FAGL_FCV) | Goods receipts posted and invoiced for a purchase order, with a difference in the GR/IR account. An open item in a non-GBP currency exists. | Company code 1000, GR/IR clearing account from your chart of accounts, one open EUR supplier or customer item | GL accountant | 1 | F.13: run automatic clearing on the GR/IR account for company code 1000, test run first | Test run lists the matching goods receipt and invoice items that will clear
[7 empty] | 2 | F.13: repeat as a live run | Clearing document created. Matched GR/IR items no longer appear as open items
[7 empty] | 3 | FAGL_FCV: run foreign currency valuation for company code 1000 as a test run, then as a live run | Valuation list shows the open EUR item with an unrealised gain or loss. Posting documents created
[7 empty] | 4 | FB03: display the valuation document | Posting is to the unrealised exchange gain or loss account and the balance sheet adjustment account. If the valuation method reverses, the reversal posts on the first day of the next period
FI-05 | Record to report | FI/CO | Capitalise an asset from a purchase order and run depreciation (AFAB) | Asset class and depreciation areas configured. Purchase order with asset account assignment is received and invoiced. | Supplier 200150, asset purchase GBP 12,000.00 net, company code 1000, cost centre 4100 | Fixed asset accountant | 1 | ME21N: create a purchase order for the asset with account assignment category A and a new asset master | Purchase order saved. Asset number is assigned and the order is account assigned to the asset
[7 empty] | 2 | MIGO: post the goods receipt for the order, then MIRO: post the invoice | Goods receipt and invoice documents created. Asset acquisition value is GBP 12,000.00
[7 empty] | 3 | Asset Explorer (AW01N): display the asset | Acquisition cost shows GBP 12,000.00 in the book depreciation area. Cost centre 4100 is the responsible cost centre
[7 empty] | 4 | AFAB: run depreciation posting for the period as a test run, then live | Depreciation document created. Expense posts to the depreciation account and cost centre 4100, and the credit goes to accumulated depreciation. Amount matches the asset class useful life
FI-06 | Record to report | FI/CO | Run the cost centre assessment cycle and check plan against actual (KSU5) | Assessment cycle defined with sender and receiver cost centres. Costs posted to the sender cost centre. | Sender cost centre 4100, receiver cost centres from your cycle, current period | Management accountant | 1 | KSB1: display actual line items on cost centre 4100 for the period and note the total | Total actual cost on cost centre 4100 is recorded before the cycle
[7 empty] | 2 | KSU5: execute the assessment cycle for the period as a test run | Test run shows the sender amount allocated to the receiver cost centres by the configured tracing factor
[7 empty] | 3 | KSU5: execute the cycle as a live run | Cycle completes with no errors. Sender cost centre 4100 is credited and receiver cost centres are debited by the same total
[7 empty] | 4 | Run the cost centre plan against actual report for cost centre 4100 | Sender cost centre balance is nil after allocation. Variance against plan is shown for each receiver cost centre
MM-01 | Procure to pay | MM | Purchase requisition to purchase order through the release strategy (ME51N, ME21N, ME29N) | Release strategy configured with an approval value threshold. Approver role assigned. | Material FG-2201, plant 1000, quantity 100, supplier 200150, net value above the approval threshold | Buyer and approver | 1 | ME51N: create a purchase requisition for material FG-2201, quantity 100, plant 1000 | Requisition number issued. Delivery date and purchasing group populated
[7 empty] | 2 | ME21N: create a purchase order for supplier 200150 referencing the requisition | Order saved. Status shows blocked or not released because the value exceeds the threshold
[7 empty] | 3 | ME29N: approver releases the purchase order | Release status changes to released. Order is now available for goods receipt
[7 empty] | 4 | ME23N: display the purchase order and check the history | Requisition is shown as converted to the order. Order quantity is 100 and the net price matches the info record
MM-02 | Procure to pay | MM | Goods receipt against the purchase order (MIGO, movement type 101) | Released purchase order for material FG-2201 exists. | Purchase order from MM-01, material FG-2201, plant 1000, quantity 100 | Warehouse operative | 1 | MIGO: select Goods Receipt and Purchase Order, then enter the purchase order number | Order items are proposed with movement type 101 and the open quantity of 100
[7 empty] | 2 | Confirm quantity 100, storage location and set the item OK, then post | Material document and accounting document created
[7 empty] | 3 | MMBE: display stock overview for FG-2201 at plant 1000 | Unrestricted stock has increased by 100
[7 empty] | 4 | FB03: display the accounting document | Debit to inventory and credit to GR/IR clearing at the order price
MM-03 | Procure to pay | MM | Three-way match invoice within tolerance (MIRO) | Goods receipt posted against the purchase order. Price and quantity tolerances configured. | Supplier 200150, purchase order from MM-01, invoice for 100 units, VAT code for standard rate 20% | Accounts payable accountant | 1 | MIRO: enter invoice date, supplier invoice reference and gross amount, then select the purchase order | Order and goods receipt items are proposed with quantity 100
[7 empty] | 2 | Enter the invoice with the price within tolerance and check the VAT amount | Balance shows 0.00. VAT is calculated at 20% on the net amount. No blocking indicator is set
[7 empty] | 3 | Post the invoice | Invoice document created. Payment block is not set
[7 empty] | 4 | FB03: display the accounting document | Debit to GR/IR clearing and input VAT. Credit to supplier 200150 for the gross amount
MM-04 | Procure to pay | MM | Invoice blocked for a price variance, then released (MIRO, MRBR) | Price tolerance configured so that a variance above the limit blocks the invoice. | Supplier 200150, purchase order with goods receipt, invoice price above the order price by more than the tolerance | Accounts payable accountant and invoice approver | 1 | MIRO: enter an invoice with the unit price above the order price beyond tolerance | System warns of a price variance and sets the invoice to blocked for price
[7 empty] | 2 | Post the invoice | Invoice posts with a payment block. Supplier line carries a blocking reason of price
[7 empty] | 3 | MRBR: select blocked invoices and release the invoice as the approver | Block is removed. Release is recorded against the approver's user ID
[7 empty] | 4 | FBL1N: display supplier 200150 line items | Invoice line has no payment block and is available for the next payment run
MM-05 | Procure to pay | MM | Stock transport order between two plants | Two plants set up with a supply relationship. Stock of FG-2201 available in the supplying plant. | Supplying plant 1000, receiving plant 2000 (placeholder), material FG-2201, quantity 50 | Purchaser and warehouse operative | 1 | ME21N: create a stock transport order with receiving plant 2000 and supplying plant 1000 for FG-2201, quantity 50 | Order saved with the stock transport order document type. No supplier is entered
[7 empty] | 2 | Post the goods issue from the supplying plant against the order | Stock in plant 1000 reduces by 50 and stock in transit increases by 50
[7 empty] | 3 | MIGO: post the goods receipt at the receiving plant | Stock in transit reduces to 0. Unrestricted stock in plant 2000 increases by 50
[7 empty] | 4 | MMBE: display the stock overview for FG-2201 | Plant 1000 is down 50, plant 2000 is up 50, and nothing remains in transit
MM-06 | Procure to pay | MM | Return goods to the supplier (MIGO, movement type 122) | Goods receipt posted for material FG-2201 and some stock still in the plant. | Supplier 200150, purchase order from MM-01, material FG-2201, plant 1000, return quantity 10 | Warehouse operative | 1 | MIGO: select Return Delivery and Purchase Order, then enter the order number | Movement type 122 is proposed with the original order items
[7 empty] | 2 | Enter return quantity 10 with a reason for movement and post | Material document created and the accounting document is created
[7 empty] | 3 | MMBE: display stock overview for FG-2201 at plant 1000 | Unrestricted stock reduced by 10
[7 empty] | 4 | ME23N: display the purchase order history | History shows the goods receipt of 100 and the return of 10, leaving a net delivered quantity of 90
SD-01 | Order to cash | SD | Standard order to cash: sales order, delivery, goods issue and billing (VA01, VL01N, VF01) | Customer 100234 and material FG-2201 extended to the sales area. Stock available. | Customer 100234, material FG-2201, quantity 20, plant 1000 | Sales order clerk, warehouse operative and billing clerk | 1 | VA01: create a standard sales order for customer 100234, material FG-2201, quantity 20 | Order saved. Confirmed quantity is 20 and the net value and VAT are calculated
[7 empty] | 2 | VL01N: create the outbound delivery with reference to the sales order, then pick and post goods issue | Delivery created. Goods issue posted and stock reduced by 20
[7 empty] | 3 | VF01: create the billing document from the delivery | Invoice created for 20 units. Accounting document posts debit to customer 100234, credit to revenue and output VAT
[7 empty] | 4 | VA03: display the sales order document flow | Flow shows order, delivery, goods issue and invoice, all with status completed
SD-02 | Order to cash | SD | Sales order blocked by the credit check and released by the credit controller | Credit limit for customer 100234 set low enough that the order exceeds it. | Customer 100234, credit limit GBP 5,000.00, order value above the limit | Sales order clerk and credit controller | 1 | VA01: create a sales order for customer 100234 with a value above the credit limit and save | Order saves with a credit block. The delivery block or credit status is shown on the order
[7 empty] | 2 | VL01N: try to create a delivery for the blocked order | Delivery cannot be created while the order is credit blocked
[7 empty] | 3 | As the credit controller, review the blocked order in credit management and release it | Credit status changes to released and the release is logged against the controller's user ID
[7 empty] | 4 | VL01N: create the delivery again | Delivery is created for the full order quantity
SD-03 | Order to cash | SD | Partial delivery with the balance left on backorder | Stock of FG-2201 is less than the ordered quantity. | Customer 100234, material FG-2201, order quantity 100, available stock 60, plant 1000 | Sales order clerk and warehouse operative | 1 | VA01: create a sales order for 100 units of FG-2201 | Order saved with a confirmed quantity of 60 and an open quantity of 40
[7 empty] | 2 | VL01N: create a delivery for 60 and post goods issue | Delivery posts for 60 units and stock reduces by 60
[7 empty] | 3 | VA03: display the sales order | Order status is partially delivered. Open quantity of 40 remains on a schedule line
[7 empty] | 4 | VF01: bill the delivery | Invoice is raised for 60 units only. Order remains open for the balance of 40
SD-04 | Order to cash | SD | Customer-specific price, discount and VAT determination | Customer-specific price and discount condition records created (VK11). Tax classification set on the customer and material. | Customer 100234, material FG-2201, list price GBP 50.00, agreed price GBP 45.00, 5% volume discount, quantity 100, UK VAT 20% | Sales order clerk | 1 | VA01: create a sales order for customer 100234, material FG-2201, quantity 100 | Item price proposes at the customer-specific GBP 45.00 and not the GBP 50.00 list price
[7 empty] | 2 | Open the item conditions screen and review the pricing | The 5% discount applies. Net value is GBP 4,275.00
[7 empty] | 3 | Check the tax line on the item conditions | Output VAT at 20% is GBP 855.00 and the gross value is GBP 5,130.00
[7 empty] | 4 | Save the order and display it in VA03 | Saved values match the pricing shown and no manual price changes are recorded
SD-05 | Order to cash | SD | Customer return and credit memo | Original invoice posted for customer 100234. | Customer 100234, material FG-2201, return quantity 5, original invoice from SD-01, plant 1000 | Customer service clerk, warehouse operative and billing clerk | 1 | VA01: create a returns order (order type RE) with reference to the original invoice for quantity 5 | Returns order saved with a return reason, quantity 5 and the original invoice price
[7 empty] | 2 | VL01N: create the returns delivery and post the goods receipt | Stock in plant 1000 increases by 5 and the goods movement is posted
[7 empty] | 3 | VF01: create the credit memo from the returns order | Credit memo created for 5 units. Accounting credits customer 100234 and reverses revenue and output VAT
[7 empty] | 4 | FBL5N: display customer 100234 line items | The credit memo shows as an open credit for the full gross amount
SD-06 | Order to cash | SD | Invoice output reaches the customer in the agreed format | Output determination set up for the customer. Customer email address and output channel maintained. | Customer 100234, invoice from SD-01, agreed format PDF by email | Billing clerk | 1 | VF02: open the invoice and check the output | Output is proposed for customer 100234 with the agreed channel and form
[7 empty] | 2 | Trigger or confirm the output has been processed | Output status shows processed successfully with no error log
[7 empty] | 3 | Open the output preview | Form shows the correct customer address, invoice number, line items, VAT breakdown and total in GBP
[7 empty] | 4 | Check the mailbox of the test customer email address | Email received with the PDF attached. The invoice number and total match the SAP document
HR-01 | Hire to retire | HR/Payroll | Hire a new starter and include them in their first payroll (PA40) | Payroll area and pay scale set up. Payroll control record open for the period. | Test employee with placeholder personnel number, start date on the first of the month, monthly salary GBP 3,000.00, test NI number and tax code | HR administrator and payroll administrator | 1 | PA40: run the Hiring action with the start date and enter the organisational assignment, personal data and payroll data | Action completes and a personnel number is issued
[7 empty] | 2 | PA30: enter basic pay, bank details and tax and NI details | Infotypes save with no errors. Basic pay is GBP 3,000.00 a month
[7 empty] | 3 | Run payroll for the period for this employee only | Payroll completes with no errors and the employee has a result for the period
[7 empty] | 4 | PC_PAYRESULT: display the payroll result | Gross pay is GBP 3,000.00. Tax, employee NI and net pay are calculated and payable by bank transfer
HR-02 | Hire to retire | HR/Payroll | Process a leaver and calculate final pay | Active employee with a full month of pay history and accrued holiday. | Test employee, leaving date mid-month, accrued untaken holiday of 3 days | HR administrator and payroll administrator | 1 | PA40: run the Leaving action with the leaving date and reason | Employment status changes to withdrawn from the leaving date
[7 empty] | 2 | Enter the payment for the untaken holiday in the payroll data | Holiday payment is saved for the final period
[7 empty] | 3 | Run payroll for the final period | Payroll completes with no errors. Salary is pro-rated to the leaving date and the holiday pay is included
[7 empty] | 4 | PC_PAYRESULT: display the payroll result | Gross pay equals pro-rated salary plus holiday pay. A leaver indicator is set and the tax and NI are correct for the period
HR-03 | Hire to retire | HR/Payroll | Backdated pay rise triggers the correct retro calculation | Employee already paid for the previous periods at the old rate. | Test employee, old salary GBP 3,000.00 a month, new salary GBP 3,200.00 a month, effective two months ago | HR administrator and payroll administrator | 1 | PA30: change basic pay to GBP 3,200.00 with a start date two months ago | Infotype saves and a retroactive accounting trigger date is set
[7 empty] | 2 | Run payroll for the current period | Payroll goes back to the earlier periods and recalculates. No errors are reported
[7 empty] | 3 | PC_PAYRESULT: display the current result | Retro difference of GBP 400.00 is shown (GBP 200.00 for each of 2 periods), along with the new current period pay at GBP 3,200.00
[7 empty] | 4 | Check tax and NI on the result | Tax and NI are recalculated on the cumulative gross pay for the year to date
HR-04 | Hire to retire | HR/Payroll | Sickness absence flows through to statutory sick pay | Employee has a qualifying pay history. Statutory sick pay rules configured. | Test employee, 8 consecutive calendar days of sickness absence | HR administrator and payroll administrator | 1 | PA30: create a sickness absence record (infotype 2001) for 8 consecutive calendar days | Absence saves with the absence type sickness and the correct dates
[7 empty] | 2 | Run payroll for the period | Payroll completes with no errors and the absence is picked up
[7 empty] | 3 | PC_PAYRESULT: display the payroll result | Statutory sick pay is calculated for the absence under the current SSP rules and rate, and agrees to a manual calculation
[7 empty] | 4 | Check basic pay on the result | Basic pay is reduced for the absence days so that no sick day is paid twice
HR-05 | Hire to retire | HR/Payroll | Run payroll and post the results to finance (posting run PC00_M99_CIPE) | Payroll run completed and exited for the period with no open errors. Wage type to GL account mapping configured. | Payroll area and period under test, company code 1000, cost centre 4100 | Payroll administrator and GL accountant | 1 | Run the payroll for the period for the whole payroll area and check the log | Log shows all employees processed and the error count is 0
[7 empty] | 2 | PC00_M99_CIPE: create a posting run as a simulation | Simulation lists the documents to post, with expense, liability and cost centre lines. Debits equal credits
[7 empty] | 3 | PC00_M99_CIPE: create the live posting run and release it for posting to finance | Run status shows documents created. Posting documents exist in company code 1000
[7 empty] | 4 | FB03: display a posted document and compare it to the payroll totals | Gross pay, employer NI and pension expense post to the expense accounts and cost centre 4100. Net pay, tax, NI and pension post to liability accounts, and totals agree to the payroll report
HR-06 | Hire to retire | HR/Payroll | RTI Full Payment Submission generated after the UK payroll run | Payroll run exited. RTI settings and the test HMRC credentials or test gateway are configured. | Payroll area and period from HR-05, test employer reference | Payroll administrator | 1 | Run the RTI Full Payment Submission programme for the period | Submission is generated with no errors and a log entry is written
[7 empty] | 2 | Review the submission content for a sample of employees | Gross pay, tax, NI, tax code and payment date match the payroll results for those employees
[7 empty] | 3 | Check the totals on the submission against the payroll report | Employee count and total pay agree to the payroll report for the period
[7 empty] | 4 | Send the submission to the test gateway and check the response | Acknowledgement is received with a status of accepted and no HMRC errors

## Defect Log
Defect ID | Script ID | Step | Date raised | Raised by | Process | Summary | Steps to reproduce | Expected | Actual | Severity | Status | Assigned to | Fix transport | Retest date | Retest result | Closed date | Status values
DEF-001 | [16 empty] | Open
DEF-002 | [16 empty] | In analysis
DEF-003 | [16 empty] | Fix in progress
DEF-004 | [16 empty] | Ready for retest
DEF-005 | [16 empty] | Closed
DEF-006 | [16 empty] | Deferred (agreed workaround)
DEF-007 | [16 empty] | Rejected (not a defect)
DEF-008
DEF-009
DEF-010
DEF-011
DEF-012
DEF-013
DEF-014
DEF-015
DEF-016
DEF-017
DEF-018
DEF-019
DEF-020
DEF-021
DEF-022
DEF-023
DEF-024
DEF-025
DEF-026
DEF-027
DEF-028
DEF-029
DEF-030

## Sign-Off
Process | Process owner | Scope tested | Scripts planned | Executed | Passed | Failed | Blocked | Open critical | Open high | Open medium/low | Conditions and workarounds | Decision (Accept / Accept with conditions / Reject) | Signature | Date
Procure to pay
Order to cash
Record to report
Hire to retire
Interfaces
Data migration
Go-live readiness
Overall recommendation
Open conditions | Owner | Due date
Steering committee decision (Go / No go)
Chair
Date